## Project Details
Product Name | Cognitive Assistant for Networks(CAN) Release 4.0 UAT Testing
Version | Release 4.0
URL | http://168.63.237.77:8011/CAN/
Created By | Reshmi Murali (AVT041)
Date of Creation | 2019-07-08
UAT Testing:
Start Date: 08-07-2019
End Date: 08-07-2019

## UAT Test Scenarios
Sl. No. | Requirement Details | Description | Status | Defect | Comments
User as a User
1 | Login | Login functionality with valid username and password, policy, password change. | Pass
2 | Predictive Fault Analysis | Provide the prediction report with the probability and priority in the format as defined in advanced configuration. The field set must match as defined in advanced configuration accessible to a developer environment for user as a developer. | Pass
| Predictive Fault Analysis -Report downloading | Reports download for filtered, daily and matched data | Pass
| Predictive Fault Analysis -Mapview | Map view of the failures and prediction | Pass with remarks |  | Map view available on cases where lat and longitudes are defined. This is specific to customer requirement
3 | Predictive Fault Analysis-> Predictive fault handling action tracking | View option to show recommended technicians to who the predictive ticket may be assigned. Allows technicians to fill up his feedback about field action that was taken. | Pass with remarks |  | Default data for technician details to be updated. 2 week timeline to be updated in demo environments.
4 | Cross Domain Correlation | Allow configuration of clustering parameters, Bit pattern view & Map view, Cluster information should be put into “Cluster” attribute of predicted fault table immediately after generation of Predicted faults. | Pass
5 | Root Cause Prediction | Root causes based on Technical Analysis and Root causes based on Field Learning. Uploading of external data under Technical Analysis and Field Learning | Pass
6 | Announcement | Display of prediction with option for full screen display | Pass
7 | Fault Analysis | Display of closed alarms along with filtering options based on Network, Operator and Locality along with map view | Pass with remarks |  | Map view available on cases where lat and longitudes are defined. This is specific to customer requirement
8 | Technician Work Plan | Provides recommendation of technicians with their credentials and the details of the alarms they resolved in the past | Pass with remarks |  | Default data for technician details to be updated. 2 week timeline to be updated in demo environments.
9 | Inventory planning | Maps the prediction with the available inventory | Pass with remarks |  | Default data for inventory details to be updated. 2 week timeline to be updated in demo environments.
User as an Administrator
10 | User Management | For managing roles, users and the view the user logs. Creating, modifying and deleting new user. Specifying view rights along with duration of the roles. | Pass
11 | Monitoring-> Data Collection Audit | An option to view Information for current month, current with previous month and current with previous 2 months would be available. | Pass
12 | Monitoring-> Notification Handler | Configuration of success & failure Email template for alarm archival, data collection, file availability and fault trace generation. | Pass
13 | Settings -> Cause Management | To map causes to specific display names for the sake of simplifying the cause list | Pass with remarks |  | This is an old feature and works on field
14 | Settings -> Announcement Exclusion Rules | To create rules related to display of predictions | Pass
15 | Settings -> Technician availability | Details and availability of technicians to be displayed along with search option | Pass
16 | Settings -> Mailing list | Defining mailing list for periodic notifications | Pass
17 | Equipment component configuration | Map the equipment details with the latitude and longitude. Search option for the equipment name. Option to upload and download equipment list | Pass
User as a Developer
18 | File collection interface | To configure new, modify and delete the file collection source along with required credentials and link it with mapper, scheduling the file collection from defined sources | Pass
19 | Data Load->Prediction->Report Generation(Main Testing) | The complete process. Dataloading, Prediction and then Report Generation | Pass |  | This is a one time activity during initial implementation. The UX functionalities are executed directly over console to check the possibilities of errors while parsing the data and subsequent processing. This is a matching/fine tuning activity to ensure matching of CAN with the incoming customer data
20 | Data Source Type addition in Parser | Modelling of data in the parsers for alarm data, ticket data , performance counter data and other types of data. Mapping of mandatory and optional fields that will be generated in the reports. Setting the file level information providing name, description, filetype, page size etc | Pass
21 | Input mapper -> Pre processor and post processor | For modifications that need to be done before and after parsing respectively | Pass
22 | Prediction assignment configuration | Load distribution for the data processing. Visibility of available nodes, policy recommendations and option to update the modification of cause id allocation specific to the nodes | Pass
23 | Filter Configuration | Option to add new data filtering rules, browse and delete rules | Pass
24 | Post prediction process | File upload to modify the data post production in case of any such scenarios, drag and drop functionality | Pass
25 | Advanced configuration screen | Define the parameters for Performance KPI, User management, archive data, matching configuration, advanced prediction, visual preference, algorithm configuration, cross domain correlation and general configuration | Pass
26 | RoE index based prediction shortlisting | Define weightage configuration, sheet configuration | Pass
27 | Alarm Filtering configuration | Allow configuration of inclusion and exclusion parameters.Sub-expression should be supported. Filter configuration would also allow to schedule a job to segregate data once the query is changed. | Pass
28 | Resource File load | Show list of files which are uploaded and also the number of records which have been processed | Pass
29 | Report Configuration | Define different types of reports like excel single page report or worksheet report of multiple pages.Need to generate reports that contain the defined fields as mentioned in UX/UI and in the same format as a single excel sheet or multiple excel worksheet. Option to select the report stationery | Pass
30 | Freeze Header pane option in excel report configuration | Once report is generated, the header will have a fixed position on top even if the end user scrolls down | Pass

## Defects
Defect ID | Defect HeadLine | Test Level (Functional/Regression) | Prerequisites and Steps to Follow | Priority/ Severity | Assigned To | Defect Status | Comments | Screenshots for reference

## Report
STATUS REPORT
UAT Test Scenarios | 30
No .of Test scenarios passed | 30
No.of Test scenarios failed | 0
Defect Status
Total Defects Raised | 0
No. of Open Defects | 0
Defect Status